## Feuil1
Rivetting sequence
preparation
install 1" grommet in F7101 and side skin for fuel line
install nutplates on f715 outer ribs + bagage bulkheads + 902 bulkhead and gussets |  | interference met side skin rivets ? Dit nu wel doen? Dan zou later doen maar weet niet of je ze dan nog kan squeezen
'Pre-rivet' the F-704H Center Section Side Plate (DWG 11) to the F-770 skin. | see manual |  | inner rivets behalve onderste vooraan = blind, achterste mag an470 |  | http://www.jasonbeaver.com/rv7/2010/02/forward-fuselage-prep.html | file:///D:/vans%20aircraft/Dan%20Checkoway/Dan's%20rvproject/rvproject/20021203.html
Rivet the F-684 Gussets to the vertical firewall angles as shown on DWG 23, Detail A. |  | 3" yoke | shop heads on outside (nicer)
Rivet the F-71 01 Gear Attach Web to the F-902 bulkhead (DWG 23, Sect G-G'.) |  | remember doubler !
Rivet the F-719 and F-719B Stiffener and Angle Clip to the vertical angle of the firewall. |  |  | misschien eerst aan angle en dan voor side skin dichtmaakt ook aan firewall ? Beweging op down?
rivet F715 outer ribs to center fuselage bottom skin
rivet F715 tot 705 bulkhead (top 2 rivets only !)
install 6 bolts on each side of F704 where 7A gear attaches, just bolt for RV7 |  | http://rvplane.com/?categoryid=4&dayid=451
Attention side skins ! Do not rivet completely, must apply sealant on the firewall flanges to side skin
rivet the bottom of the 901 to the lower longeron.
main assembly before bottom skin is on
bolt lower longeron to firewall an3 bolts |  | will make side rivetting more difficult but torque on these bolt is important here
rivet the lower tab on the 902 bulkhead to lower aux angle now !
rivet floor stiffeners inner to F704 and firewall angles
bolt in outboard seat rib to F705 (aan rear spar wing) nog niet installeren |  | interferes met rivetting corner rib
cut canopy deck slots so canopy deck can be isntalled for rivetting
rudder pedals position drilling !!
main assembly
set rivets between rivets on back side to attach longeron to tail cone. |  |  |  | squeezer
set all rivets Aft of where the F-709 bulkhead on longeron (where deck comes) |  |  |  | longeron yoke squeezer
rivet as many as possible on seat rib to skin and F704 through controls hole |  |  |  | squeezer
squeeze aft of baggage ribs to F706 where possible |  | normally top 2 only.
if remaining baggage ribs to shoot, do it now
sides of F704 from bottom to top |  | gun
apply sealant to firewall and cleco
from 704 forward along bottom longeron and aux longeron F717 and F713 |  | gun | all way to front but not on firewall !
bottom forward line of F704 with bottom skin
rivet F719 from f704 forward
rivet F902 bulkhead to side skin
rivet floorstiffeners from F704 to front
rivet firewall bottom angle (F601) to bottom skin
rivet F704 aft line to bottom skin
install control mount brackets to F704
rivet armrests to side skin, keep canopydecks just clecoed
rivet F722 from F705 to back
rivet F724
set top rivet F724 to longeron
rivet corner rib 623 to bottom (remember doublers) and to side skin
rivet the remaing upper bulkhead rivets in tailcone to the longeron level.
bolt itorque in outboard seat rib to F705 (aan rear spar wing)
TURN OVER THE CANOE !